## Q3
CYCLE TRACKER
PopWheels software Q3 project/cycle tracker
Project (link project doc) | Owner | Cycle 1 |  |  |  | Cycle 2 |  |  |  | Cycle 3 |  |  |  | Cycle 4
|  | 2026-06-23 | 2026-06-30 | 2026-07-07 | End of cycle deliverables (Jul. 14) | 2026-07-14 | 2026-07-21 | 2026-07-28 | End of cycle deliverables (Aug. 4) | 2026-08-04 | 2026-08-11 | 2026-08-18 | End of cycle deliverables (Aug. 25) | 2026-08-25 | 2026-09-01 | 2026-09-08 | End of cycle deliverables (Sept. 15)
PopCart phase 2 support | Samson, Ney | Planning | Planning | Paused | Webapp in testing |  |  |  | Shipped and live
Passwordless auth | Samson |  |  | Paused | (Stretch) |  |  |  | Spec done
Battery type mismatch app error message | Samson |  |  | Paused |  |  |  |  | Pending
Banner for user survey | Samson | [7 empty] | Pending
Short swap precision/recall | Yossi/Samson | Planning |  | Building | Shipped, ready for live (pending ops) |  |  |  | Pending
Short swap experiments | Yossi/Samson |  |  |  | Ongoing |  |  |  | Pending
Billing API migration | Ney | Building | Building | Building | All accounts migrated |  |  |  | Done
Whizz migrate to new transactions | Ney |  | (waiting on Whizz) | Paused | Ongoing |  |  |  | Waiting on Whizz
Detect non-charging batteries | Brian | Planning | (spec for Ney review) | Building | Shipped and live |  |  |  | In testing
Battery count v3 (lifecycle tracking) | Brian | Testing | Deployed | Planning | Shipped and live |  |  |  | Model decided
Self-serve bad battery return | Brian | Testing | Building | Building | Tested, app implementation ready for review |  |  |  | Mobile app handoff
Productionize SLA predictions | Brian |  |  | Planning | Spec done |  |  |  | In testing
Audit Hologram/cabinet uptime | Brian |  |  | Planning | Hologram dongle tested |  |  |  | Data to Hologram
Customer happiness score | Yossi/Maddie | Building |  |  | Published score |  |  |  | Tech spec done
NPS and churn data analysis | Yossi/Maddie |  |  |  | Spec done |  |  |  | Report done/flexible
Ops scanner | Yossi, Brian |  |  | Planning | (Backlog)
PopCart phase 1 support | Samson | Deployed |  |  | Friday June 26 test
False door closed report | Ney |  | Emergency | Testing | Done
Tax-related bugfix | Ney | Building | (to deploy) | Deployed | Done
Temperature alerts not coming to alarms channel | Brian |  | Emergency | Deployed | Done
Show power off slot as red | Brian | Testing |  | Deployed | Live across network
Cloud-hosted cabinet and battery firmware flashing tools | Brian | Deployed |  |  | Shipped and live

## Q2
CYCLE TRACKER
PopWheels software Q2 project/cycle tracker |  |  | Kickoff
Project (link project doc) | Owner | Goal | Cycle 1 |  |  |  | Cycle 2 |  |  |  | Cycle 3 |  |  |  | Cycle 4
|  |  | 2026-03-31 | 2026-04-07 | 2026-04-14 | End of cycle deliverables (Apr. 21) | 2026-04-21 | 2026-04-28 | 2026-05-05 | End of cycle deliverables (May 12) | 2026-05-12 | 2026-05-19 | 2026-05-26 | End of cycle deliverables (June 2) | 2026-06-02 | 2026-06-09 | 2026-06-16 | End of cycle deliverables (June 23)
Battery count v3 (working with Yosef) | Brian | [10 empty] | Building | Building | Shipped and live | Planning | Testing | Planning | Spec done
Self-serve bad battery return | Brian |  | Pending | Planning | Planning | Product spec done | Planning | Planning | Planning | Zero-Claude tech spec done | Planning | Planning | Planning | In testing | Testing | Testing | Building | Ready for review for app, live testing on webapp | Ney coming to NY
Hologram audit | Brian | [15 empty] | Planning | Report done | 2026-07-19
Charge cabinet step 2 | Brian | [15 empty] | Deployed | Give a demo | 🎉 | 🎉 | 🎉 | 🎉 | 🎉 | 🎉 | 🎉 | 🎉
Data pipeline failure (sla service compute) | Brian | [14 empty] | Emergency | Deployed
Power orchestrator updates (data) | Brian | [10 empty] | Building |  | (Deprioritized) | Deployed
Slot screen show disable test | Ney, Brian | [14 empty] | Planning | Pending | Test the feature
Dead in slot detection | Ney, Brian | [7 empty] | Testing | Test on real cabinet | Testing | Testing | Pending | Live across network | Testing | Deployed |  | Live across network
Stripe link direct onboard for ambassadors | Ney | [9 empty] | Emergency | Testing |  | (Unplanned) | Deployed
Billing coupon | Ney | [9 empty] | Testing |  |  | Shipped and live | Deployed
Performance fixes | Ney | [8 empty] | (Unplanned) | Pending |  |  | (Ongoing) | Ongoing
Transaction errors | Ney | [13 empty] | Building | Building | Deployed | (Emergency)
Whizz transaction errors | Ney | [13 empty] | Testing | Building | Pending deploy | (Emergency)
Billing API v2.1 | Ney | [14 empty] | Pending | Building | All customers migrated to new billing API
Short swap survey v2 | Yossi | [9 empty] | Pending | Pending | Building | (Yossi has finals) | Building | Building | Deployed | Ongoing
Short swap auto disable for key / lock issue | Yossi | [12 empty] | Shipped and live | Pending Ney review | Building | Deployed | Shipped and live
batteryTransaction/check problem | Samson | [9 empty] | Emergency | Planning | Building | (Bugfix) | Building |  | Deployed | Shipped and live
Send API headers from mobile app | Samson | [11 empty] | Building | (Unplanned) | Building |  | Deployed | Shipped and live
Additional app analytics | Samson | [13 empty] | Building |  | Deployed | Shipped and live
Referrals => self-serve onboarding | Samson |  | Planning | Planning | Planning | Full UI mockups and spec done | Pending | Planning | Planning | Tech spec done | Pending | Pending | Pending | (Deprioritized for PWIA) | Paused |  |  | Ready to build
Whizz partial cabinet support | Ney |  | Planning | Planning | Planning | Spec done | Pending | Pending | Pending | Tech spec done | Pending |  | Pending | (Priority) | Paused |  |  | Pending David prioritization
non active or low priority tasks below
Battery count v2 | Brian |  | Planning | Building | Planning |  | Building | Testing | Testing | In testing | Deployed |  |  | Shipped and live
Charge cabinet | Brian |  | Pending |  | Planning | Modiary cabinet back to Newlab | Testing | Testing | Testing | Charge Whizz battery through barrel plug | Pending | Testing | Deployed | Test new firmware (force charge)
Short swap survey | Yossi |  | Building |  |  | Shipped and live | Building | Building | Testing | Shipped and live | Deployed
Billing API fixes | Ney | [6 empty] | Building | Building | (Unplanned)
Firmware updates | Brian | [6 empty] | Emergency | Emergency | (No deliverable)
Admin fixes | Brian
Deployments 2.0 | Ney |  | Pending |  |  | (Stretch)
App usability fixes (sites, visible support) | Samson |  | Building | Building | Building | Shipped and live | Pending | Deployed |  | Shipped and live
New billing API app support | Samson and Ney |  | Building | Building | Building | Shipped and live | Building | Deployed |  | Shipped and live
Power drop alert | Brian |  | Building | Deployed |  | Shipped and live
Power limiting | Brian |  | Post-deployment | Post-deployment | Post-deployment | Full deployment across network
Battery summer 2026 temp analysis | Brian |  |  | Emergency | Post-deployment
Backup server down | Brian |  |  | Emergency | Deployed
Modiary cabinet development | Samson | [5 empty] | Pending | Pending | Pending | One round of testing at 123 St
Customer experience observability / battery transaction errors | Brian (pending), Ney, Maddie |  | Planning | Planning | Done | Spec done

## Q1
CYCLE TRACKER
2026 Q1 cycle tracker |  |  |  |  | Kickoff |  |  |  | Kickoff |  |  |  | Kickoff
Project (link project doc) | Owner | Goal | Cycle 0 |  | Cycle 1 |  |  |  | Cycle 2 |  |  |  | Cycle 3
|  |  | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | End of cycle deliverables | 2026-02-17 | 2026-02-24 | 2026-03-03 | End of cycle deliverables | 2026-03-10 | 2026-03-17 | 2026-03-24 | Goals
Dynamic charging | Brian | 🛠️ Ops/scale |  | Building | Testing | Testing | Testing | 3 day test at Lockaway on test server | Testing | Testing | Testing | Full scale rollout | Building | Building | Building | Live on every cabinet, Metrics dashboard deployed
Admin as source-of-truth v0.1 / respond.io sync | Brian | 📣 Customer acquisition |  | Planning | Planning | Planning | Planning | clear project spec (NOT tech spec) | Planning | Planning | Building | Design/scoping complete, week 3 implementation |  | Deployed | Post-deployment | Deploy, Post-deployment feedback from CS
MaintainX System Sync | Brian | [7 empty] | Building | Building | Building | Design complete. Target live in week 2 | Deployed but not working | Deployed | Post-deployment
Current drop alert | Brian | 🛠️ Ops/scale | [7 empty] | Planning | Planning | (no clear deliverable set) |  | Planning | Building | Fully spec’d, in testing
Maintenance transaction battery insert | Brian | [12 empty] | Planning | Blocked | Fully spec’d, in testing
Fix hanging transaction | Brian, Ney | [12 empty] | Planning | Deployed | Fully spec’d, in testing
hudson launch software | Samson | 📣 Customer acquisition |  | Planning | Building | Building | Building | web signup and new app version shipped, signup completed through new flow | n/a | n/a | Pending | Billing API dependence | Building | Building |  | Live by March 16
PopWheels+ => Zone-based pricing | Samson | 💵 Profit margins |  | Planning | Planning | Planning | Planning | product and technical product spec complete | n/a | n/a | Planning | Spec complete | Planning | Post-deployment | Post-deployment | Live by March 16, new users signing up for $95 plan
Referrals | Samson | 📣 Customer acquisition | [11 empty] | Planning | Planning | Spec complete
Short swap feedback | Yossi | 🛠️ Ops/scale | Planning | Planning | Building | Building | Building | app and web prototype | Planning | Building | Building | QA-ready prototype |  |  | Building | Deployed, post-deployment feedback
Billing API | Ney | 💵 Profit margins |  | Planning | Planning | Building | Building | shipped, manage products and subscriptions in admin, meeting samson and brian use cases | Building | Building | Building | API done, migration done, tools/management done | Building | Post-deployment | Post-deployment | Work with Samson, live by March 16
Investigate transaction problems | Ney
Dead in slot detection | Ney | [12 empty] | In production but disabled | Testing | Test and enable in production
Maintenance transaction post-deployment | Ney | [13 empty] | Post-deployment
Replace reports with metabase | David | [12 empty] | Post-deployment
PROJECTS BELOW NOT IN PROGRESS |  |  | PROJECTS BELOW NOT IN PROGRESS
Deployments 2.0 | Ney
Access control | Ney | 🔒 Security
Battery forensics tool | Samson, Brian | 🛠️ Ops/scale
Readiness for LTE batteries | Everyone | 🛠️ Ops/scale
Integrated financial penalties | Interested: yossi, brian, samson | 🛠️ Ops/scale
Bad battery return | Ney? | 🛠️ Ops/scale
Toronto Readiness | Brian | [8 empty] | Emergency |  | Escalated to and resolved by CEO
Whizz errors | Ney, Brian |  |  | Emergency | Emergency | Emergency
Guarantee empty slots / availability alarm | Ney, Brian |  |  | Emergency |  | Emergency | Deployed
Maintenance on SLA, cell divergence alarms | Brian | [5 empty] | Deployed
Rack gateway performance | Ney |  |  |  | Emergency | Emergency | Testing
Non-building containers | Ney |  |  |  | Emergency | Deployed
Map-first app launch | Samson | 🛝 Customer usability | Deployed
2x Whizz Bugs | Ney | [8 empty] | Emergency
Dead-in-the-slot battery | Ney | [8 empty] | Emergency
"No empty slots" false alarm fix | Brian | [8 empty] | Emergency

## demo
CYCLE TRACKER
2026 Q1 cycle tracker |  |  |  |  | Kickoff |  |  | Kickoff |  |  | Kickoff
Project (link project doc) | Owner | Goal | Cycle 0 |  | Cycle 1 |  |  | Cycle 2 |  |  | Cycle 3
|  |  | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24
Map-first app launch | Samson | 🛝 Customer usability | 2026-01-13: Deployed
PopWheels+ | Samson | 💵 Profit margins | 2026-01-13: Planning
Referrals | Samson | 📣 Customer acquisition
Dynamic charging | Brian | 🛠️ Ops/scale | 2026-01-13: Building
Short swap feedback | Yossi | 🛠️ Ops/scale | 2026-01-13: Planning
Current drop alert |  | 🛠️ Ops/scale
Battery forensics tool |  | 🛠️ Ops/scale
Bad battery return |  | 🛠️ Ops/scale
Integrated financial penalties |  | 🛠️ Ops/scale
Admin source of truth for customer data |  | 📣 Customer acquisition
Streamilne customer onboarding for Hudson launch |  | 📣 Customer acquisition
Clean up waitlist flow |  | 📣 Customer acquisition
Billing API | Ney | 💵 Profit margins | 2026-01-13: Building
Readiness for LTE batteries |  | 🛠️ Ops/scale
Access control |  | 🔒 Security